## Budget Checklist
2-Story Steel Building — Pre-Construction Budget Checklist
Budget items most buyers forget ¦ All prices in USD ¦ US market 2025 ¦ Sources: RSMeans 2024–25 · PEMB manufacturers · ACEC fee survey · IBC 2021 · ASCE 7-22
✏ Enter your budgeted amount in column E (Your Budget). The Status column updates automatically. Mark ✓ in column A once confirmed with your contractor.
✓ | Budget Item | Low Est. (USD) | High Est. (USD) | Your Budget (USD) | Status | Why It Gets Missed | Code / Standard
📋 PRE-CONSTRUCTION & PROFESSIONAL FEES
☐ | Geotechnical (Soil) Report | 1500 | 5000 |  |  | Skipped to save $2–5K; remediation after pour costs $20–80K | ASCE 7-22 §11 — required for uplift-rated two-story foundation design
☐ | Licensed Structural Engineer (PE) Fees | 5000 | 20000 |  |  | Assumed included in kit price — almost never is for two-story builds | IBC 2021 §1604 — PE stamp mandatory for multi-story occupied structures
☐ | Architect Fees (jurisdictions that require it) | ~7% of construction cost | See left column |  |  | Discovered at permit stage; required in many cities for commercial occupancy | IBC 2021 §107 — construction docs must be by licensed design professional
☐ | Building Permits — Two Occupied Levels | 1500 | 5000 |  |  | Buyers use single-story permit cost as baseline; two-story review costs more | IBC 2021 §105 — full plan review required per occupied floor in most jurisdictions
🏗 SITE WORK & FOUNDATION
☐ | Site Preparation, Grading & Land Clearing | 3000 | 25000 |  |  | Buyers assume site is ready; it rarely is — slope, trees, and fill add cost | IBC 2021 §1804 — compacted, level bearing surface required before slab pour
☐ | Foundation Upgrade — Uplift-Rated Footings (Two-Story) | 15000 | 40000 |  |  | Buyers budget single-story slab cost; uplift design alone adds $15–40K | ASCE 7-22 §12.14 — foundation must resist ≥60% of dead load as uplift force
☐ | Utility Connections (Water, Sewer, Electric, Gas) | 5000 | 30000 |  |  | Distance to street varies — can be $500 or $30,000; never in kit quote | NEC 2023 Art. 230 (electrical service entrance); local utility authority rules
🔩 STRUCTURAL ITEMS UNIQUE TO TWO-STORY BUILDS
☐ | Second Means of Egress — Code-Compliant Steel Staircase (×2) | 6000 | 24000 |  |  | Single-story needs no stair; two-story requires min. two egress routes | IBC 2021 §1006.3 — two exits required when second-floor occupant load exceeds 10
☐ | ADA Elevator or Platform Lift (public-occupancy buildings) | 25000 | 65000 |  |  | Legally required but never in a kit quote; often caught only at permit review | ADA Standards §206 + IBC 2021 §1009 — accessible route to all occupied floors
☐ | Floor Framing System — Upper Level (per sq ft of upper floor) | $12 – $25 / sq ft | See left column |  |  | Entirely absent in single-story; buyers forget this is a full structural system | AISC 360-22 §B3 — floor framing designed for live + collateral load combinations
🔥 MECHANICAL, ELECTRICAL & FIRE SYSTEMS
☐ | Fire Sprinkler System (triggered by occupancy / sq ft threshold) | 15000 | 45000 |  |  | Auto-triggered in most commercial occupancies over 5,000 sq ft total area | IBC 2021 §903 + NFPA 13 — automatic sprinkler required in most B / M / S groups
☐ | HVAC System — Both Levels (zoned units or full ducted system) | 15000 | 60000 |  |  | Always excluded from steel building kits; two-story requires separate floor zones | ASHRAE 90.1-2022 energy compliance — each floor requires independent zone control
☐ | Electrical Service Upgrade & Second-Floor Sub-Panel | 8000 | 25000 |  |  | Two-story often needs 400A service vs. 200A; panel location must be replanned | NEC 2023 Art. 220 — load calculation must cover both floors independently
🏠 INSULATION & BUILDING ENVELOPE
☐ | Full Building Envelope Insulation (walls, roof deck, floor deck) | $2 – $5 / sq ft installed | See left column |  |  | Never included in any standard steel building kit price — always extra | IECC 2021 / ASHRAE 90.1-2022 — minimum R-values by climate zone; larger envelope in two-story
SUBTOTAL — ALL ITEMS
PRIORITY COLOUR: 🔴 Red = Legally required or causes $20K+ cost overrun if missed ¦ 🟡 Amber = Important, easy to underestimate ¦ 🟢 Green = Separate from kit, but predictable
STATUS LEGEND: ⚠ Not Budgeted = enter an amount ¦ 🔴 Below Low Est. = may be insufficient ¦ 🟢 Within Range = reasonable ¦ 🔵 Above High Est. = conservative budget
DATA SOURCES: RSMeans Construction Cost Data 2024–25 · ACEC Engineering Fee Survey · Allied Steel / National Steel / American Steel published pricing (2025) · IBC 2021 · ASCE 7-22 · AISC 360-22 · NEC 2023 · ASHRAE 90.1-2022 · ADA Standards 2010